## Slide 1: Sauce & Spoon Tablet Rollout
Impact Report

## Slide 2: Executive Summary
The tablet rollout fulfilled the need to improve the sales of the two chosen locations (North and Downtown branches) by decreasing the amount time it takes for the customers to wait for their order. The food waste also decreased because of the accuracy of the orders made directly from the tablets
Two key milestones helped us achieve this project:
  The integration of the POS softwares to our tablets that made an increase of our customer satisfaction, and
  The efficiency and accuracy of the orders made due to a centralized flow of information (from guests to kitchen)
Two things could’ve been done right for this project:
  Secure a more suitable vendor to prevent sudden contract updates and overspending, and,
  Improve our order accuracy to ensure the downward trend of our food waste
Two steps for the next chapter:
  Tablet rollout for the other locations
  More training and workshop for our staffs and personnel

## Slide 3: Customer Satisfaction: Pilot
Q. On a scale of 1-5, please rate your experience with the tablet overall.
This pie chart illustrates the results from the post-pilot survey.
72% of respondents indicated a customer satisfaction score of 4 or 5.
Notes: First pie chart: Results from the post-pilot survey
Second pie chart: Results from the post-launch survey, after making changes
Satisfaction has gone up from 72% (4 and 5 rating) to 86% (4 and 5 rating)
Post-pilot data:
1 - Lacking 2 4%
2 5 10%
3 7 14%
4 20 40%
5 - Great 16 32%
Post-launch data:
1 - Lacking 1 2%
2 2 4%
3 4 8%
4 22 44%
5 - Great 21 42%

## Slide 4: Customer Satisfaction: Launch
Q. On a scale of 1-5, please rate your experience with the tablet overall.
This pie chart illustrates the results from the post-launch survey.
86% of respondents indicated a customer satisfaction score of 4 or 5. This is a 14% increase.
Notes: First pie chart: Results from the post-pilot survey
Second pie chart: Results from the post-launch survey, after making changes
Satisfaction has gone up from 72% (4 and 5 rating) to 86% (4 and 5 rating)
Post-pilot data:
1 - Lacking 2 4%
2 5 10%
3 7 14%
4 20 40%
5 - Great 16 32%
Post-launch data:
1 - Lacking 1 2%
2 2 4%
3 4 8%
4 22 44%
5 - Great 21 42%

## Slide 5: Revenue
Tablet Launch April 23
This is a chart of Sauce & Spoon revenue, showing that after tablet implementation, revenue increased.
July revenue was up to 20% over April’s monthly revenue.
Notes: This is a chart of Sauce & Spoon revenue, showing that after tablet implementation, revenue increased. December revenue was up to 20% over September’s monthly revenue.
Sales data:
October
$61,000.00
November
$62,000.00
December
$62,000.00
January
$63,000.00
February
$64,000.00
March
$61,000.00
April
$65,000.00
May
$70,000.00
June
$75,000.00
July
$78,000.00

## Slide 6: What Worked: Key Accomplishments
Decreased table turn time
Implementation of the tablets increased the average daily guest count by 10%.
Tablets also decreased wait time by 30 minutes.
Decreased food waste
Tablets identified who was receiving an incorrect order.
Kitchen staff has taken the initiative to correct orders and decrease food waste by 50%.
Increased customer satisfaction
After the pilot, customer satisfaction was at 72%.
Once we implemented improvements based on feedback, customer satisfaction increased to 86%.
Increased sales
Our monthly revenue has increased steadily since the tablet rollout, upwards of 20% since September/pre-rollout.
Tablets also helped boost revenue during the holiday season.

## Slide 7: Next Steps: Looking Forward
Initiative | Action | Date
Implement tablets in more locations | Create new project plan for new location installation | Q2
Continue to track customer experience and satisfaction | Continue surveying/ gathering data through various means | Ongoing
Expand tablet features | Investigate new features like social media integration, reservations, videos, etc. | Q4

## Slide 8: Appendix Access all resources here.
Notes: Insert link to your shared drive or a shared folder with all of the relevant project artifacts