## Tasks and Timeline
Terrific Tablets Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1: Terrific Tablets Project Initiation | Task Owner TBA
1.1 Research key data sets re: reservation systems and other matters
1.2 Gather data on booking process from previous or other similar projects
1.3 Align and evaluate stakeholders including waitstaff and GMs
1.4 Calculate projections and enhancements
1.5 Interview members of the staff
1.6 Create project charter (scope and goals)
1.7 Schedule kick off meeting
Milestone 2: Tablet Sourcing | Task Owner TBA
2.1 Research reservation system options
2.2 Generate quotes and review costs
2.3 Test out reservation systems
2.4 Choose a reservation system
2.5 Timeline and Deliverable Charts
Milestone 3: Project Planning | Task Owner TBA
3.1 Create contracts and SoWs
3.2 Project Plan Updates
3.3 Update marketing/social media plan/calendar
3.4 Create launch day plan
Milestone 4: Training Plan and Project Launch | Task Owner TBA
4.1 Map out seating chart/upload into POS
4.2 GM Training and Workshop
4.3 Waitstaff Training and Workshop
4.4 Test run reservation system
4.5 Create troubleshoot/support plan
4.6 Launch day

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone 1: Terrific Tablets Project Initiation
1.1 Research key data sets re: reservation systems and other matters |  | 6 |  |  |  | H
1.2 Gather data on booking process from previous or other similar projects |  | 0.5 |  |  |  | H
1.3 Align and evaluate stakeholders including waitstaff and GMs |  | 1 |  |  |  | H
1.4 Calculate projections and enhancements |  | 1 |  |  |  | H
1.5 Interview members of the staff |  | 1 |  |  |  | H
1.6 Create project charter (scope and goals) |  | 3 |  |  |  | H
1.7 Schedule kick off meeting |  | 0.5 |  |  |  | H
Milestone 2: Tablet Sourcing
2.1 Research reservation system options |  | 3 |  |  |  | M
2.2 Generate quotes and review costs |  | 2 |  |  |  | M
2.3 Test out reservation systems |  | 3 |  |  |  | M
2.4 Choose a reservation system |  | 3 |  |  |  | M
2.5 Timeline and Deliverable Charts |  | 3 |  |  |  | M
Milestone 3: Project Planning
3.1 Create contracts and SoWs |  | 4 |  |  |  | H
3.2 Project Plan Updates |  | 14 |  |  |  | H
3.3 Update marketing/social media team |  | 11 |  |  |  | H
3.4 Create launch day plan |  | 10 |  |  |  | H
Milestone 4: Training Plan and Project Launch
4.1 Map out seating chart/upload into POS |  | 2 |  |  |  | M
4.2 GM Training and Workshop |  | 0.5 |  |  |  | M
4.3 Waitstaff Training and Workshop |  | 0.5 |  |  |  | M
4.4 Test run reservation system |  | 0.5 |  |  |  | M
4.5 Create troubleshoot/support plan |  | 5 |  |  |  | M
4.6 Launch day |  | 1 |  |  |  | M

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Service | More efficient waitstaff and tablet experience | Orders made correctly | Average ticket time | FALSE
Customer satisfaction | Shorter checkout time from waitstaff/tablets | One-minute checkout time | Checkout process is seamless and easy to navigate | FALSE
Experience | Positive feedbacks from overall experience | Reviews | Less than 5% of customers report technical issues each week | FALSE
Orders | Cutting down on incorrect orders | Order Returns | 98% order accuracy | FALSE
Wait time | Decreased customer wait time in the lobby | Wait time before customers are seated | Average wait time of ten minutes or less | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
More efficient waitstaff and tablet experience | Orders made correctly | Average ticket time | Did the ordering process go smoothly without any hassle? | Yes/No | Yes | No
Quicker check-out | One-minute checkout time | Checkout process is seamless and easy to navigate | Was the food delivery system satisfactory? | Scaled | 1: Very Satisfied | 2: Somewhat satisfied | 3: Neither satisfied nor dissatisfied | 4: Somewhat dissatisfied | 5: Very dissatisfied
Positive feedbacks from overall experience | Reviews | Less than 5% of customers report technical issues each week | Please state any issue that you faced, if any | Open-ended | Open-ended
Cutting down on incorrect orders | Order Returns | 98% order accuracy | Was the order done correctly? | Yes/No | Yes | No
Decreased customer wait time in the lobby | Wait time before customers are seated | Average wait time of ten minutes or less | Was the checkout process smooth and easy to follow? | Yes/No | Yes | No
Shorter checkout time from waitstaff/tablets | One-minute checkout time | Checkout process is seamless and easy to navigate | Did you face any issues with the payment gateway? | Yes/No | Yes | No
Shorter checkout time from waitstaff/tablets | One-minute checkout time | Checkout process is seamless and easy to navigate | Did you feel comfortable with the online payment method? | Yes/No | Yes | No
Decreased customer wait time in the lobby | Wait time before customers are seated | Average wait time of ten minutes or less | How much time did you have to wait untill a seat was allocated to you? | Open-ended | Open-ended
Quicker check-out | One-minute checkout time | Checkout process is seamless and easy to navigate | How much time did it take for the check out process? | Open-ended | Open-ended
More efficient waitstaff and tablet experience | Orders made correctly | Average ticket time | How much would you rate the dining experience on a scale of 1-5? | Scaled | 1: Very Satisfied | 2: Somewhat satisfied | 3: Neither satisfied nor dissatisfied | 4: Somewhat dissatisfied | 5: Very dissatisfied
More efficient waitstaff and tablet experience | Orders made correctly | Average ticket time | Would you recommend the restuarant to a friend? | Yes/No | Yes | No
Positive feedbacks from overall experience | Reviews | Less than 5% of customers report technical issues each week | How was your tablet ordering experience? | Multiple choice | Very good | Good | Ok | Bad | Very bad
Decreased customer wait time in the lobby | Wait time before customers are seated | Average wait time of ten minutes or less | The wait time was less than 10 minutes | True/False | TRUE | FALSE
Positive feedbacks from overall experience | Reviews | Less than 5% of customers report technical issues each week | Was the tablet interface easy to follow? | Yes/No | Yes | No
More efficient waitstaff and tablet experience | Orders made correctly | Average ticket time | Did you have any other isues? | Open-ended | Open-ended